## Sheet1
Chris McCracken
Week 1 Assignment
Advanced Software Engineering
1 | Dependencies | Start | Dependent On
|  | UC01 | None
|  | UC02 | UC01
|  | UC03 | UC01
|  | UC04 | UC03
|  | UC05 | UC03
|  | UC06 | UC03
|  | UC07 | UC04
|  | UC08 | UC03
|  | UC09 | UC08
2 | Iterations | Month 1 | Points 1 | Month 2 | Points 2 | Month 3 | Points 3
|  | UC01 | 1 | UC05 | 1 | UC07 | 4
|  | UC02 | 1 | UC06 | 4 | UC09 | 3
|  | UC03 | 3 | UC08 | 2
|  | UC04 | 2
This will allow 7 points of work per month with a max of 9. This will allow for some error and overrun each month
Priority is Red, Yellow, Blue in each month
3 | Top 5 Risks
| 1 | Risk: | Personnel Shortfall
|  | Resolution: | Ensure we are staffing with our best people
|  | Justification: | This is an important project that we are working on. I am assuming it is our primary source of income
| 2 | Risk: | Developing the wrong user interface
|  | Resolution: | Have regular meetings with your share holders to ensure we are moving in a direction that will be user friendly to them
|  | Justification: | We want to ensure our end product meets their needs
| 3 | Risk: | Gold-Plating
|  | Resolution: | Set a specific goal for what we want the software to accomplish and hold to it.
|  | Justification: | This project needs to come in on time and on budget. By keeping a clear goal in mind you will help that goal
| 4 | Risk: | Continuing Stream of Changes
|  | Resolution: | Set a specific goal for the the project and ensure that you lay out for the share holders what is included in the bid
|  | Justification: | If we do not hold them accountable to guidelines the project can bloat. This will make us miss our deadline and not get paid.
| 5 | Risk: | Developing the Wrong Functions and Properties
|  | Resolution: | Get with end users and share holders. Have regular testing of the software you have created to date to ensure it meets requirements.
|  | Justification: | If your software does not meet what your share holders expect then you do not get paid.